## Sheet1
Quadratic Solver Project Stories
The quadratic solver program takes three inputs from a user via a command line interface. The three inputs are real single precision numbers which the system will use and return x1 and x2 as real values using the quadratic formula. If complex roots are detected, a warning will be presented to the user. Furthermore, the system will detect bad input and display warnings if single precision isn't used by the user.
Story Description | Time Remaining | Risk | % Complete | Time Total
User enters real numbers a, b, c and x1 and x2 are returned as real values using the quadratic formula | 2 hours | 3 | 0
If the user enters values that result in complex roots, the system will display an error message to the user | 3 hours | 5 | 0
If the user enters non real numbers, the system will display an error message to the user | 2 hours | 4 | 0
If the user enters bad input, the system will report the information | 1 hour | 3 | 0
User has the ability to toggle whether errors are written to a log file through a command line argument | 2 hours | 2 | 0
If a user enters non single precision number, the system will display an error message to the user | 3 hours | 3 | 0
Risk: 1 = lowest; 5 = highest
Version Control: Git
Requirements: Compiles and runs on Linux
Compiler: GCC
Project Team: Alex Ewert, Chandler Miller, Brandon Grothe, Samuel Lewis