## Sheet1
TPS Report (10/16/2017-10/22/2017)
Task Description | Expected Time | Risk | Person | Actual Time | % Complete | Code Review
Added group members to Github repo | 10 minutes | 1 | Alex Ewert | 5 minutes | 100
Research machine absolute vs relative precision | 1 hour | 1 | Alex Ewert | 45 minutes | 100
Researching writing shell files for automation | 15 minutes | 1 | Samuel Lewis | 1 hour | 100
Research makefiles | 10 minutes | 1 | Chandler Miller | 10 minutes | 100
Create Linux Virtual Machine | 1 hour | 1 | Chandler Mller | 35 minutes | 100
Risk: 1 = lowest; 5 = highest
Version Control: Git
Project Team: Chandler Miller, Alex Ewert, Brandon Grothe, Samuel Lewis