## Sheet1
TPS Report (10/2/2017-10/8/2017)
Task Description | Expected Time | Risk | Person | Actual Time | % Complete | Code Review
Setup Github Repository | 10 minutes | 1 | Alex Ewert | 5 minutes | 100
Research absolute vs relative precision | 2 hours | 1 | Alex Ewert | 1 hour | 100
Research quadratic equation | 20 minutes | 1 | Chandler Miller | 10 minutes | 100
Research input validation | 20 minutes | 1 | Chandler Miller | 20 minutes | 100
Makefiles | 1 hour | 1 | Samuel Lewis | 15 minutes | 100
GCC options | 1 hour | 1 | Samuel Lewis | 30 minutes | 100
C-unit | 1 hour | 1 | Brandon Grothe | 1 hour | 100
IEEE Floating Point | 1 hour | 1 | Brandon Grothe | 1 hour | 100
Risk: 1 = lowest; 5 = highest
Version Control: Git
Project Team: Alex Ewert, Chandler Miller, Brandon Grothe, Samuel Lewis