## Sheet1
TPS Report (10/23/2017-10/29/2017)
Task Description | Expected Time | Risk | Person | Actual Time | % Complete | Code Review
Created the input module | 15 minutes | 1 | Samuel Lewis | 20 minutes | 100 | Alex Ewert
Integrated modules to main program | 15 minutes | 3 | Samuel Lewis | 1 hour | 100 | Alex Ewert
Created initial qsolver method | 1 hour | 3 | Alex Ewert | 15 minutes | 100 | Samuel Lewis
Added precision spike to repository | 15 minutes | 1 | Alex Ewert | 10 minutes | 100
Create Unit tests | 30 Minutes | 2 | Chandler Miller | 30 Minutes | 15
Risk: 1 = lowest; 5 = highest
Version Control: Git
Project Team: Chandler Miller, Alex Ewert, Brandon Grothe, Samuel Lewis