## Sheet1
TPS Report (10/30/2017-11/05/2017)
Task Description | Expected Time | Risk | Person | Actual Time | % Complete | Code Review
Create initial c-unit module | 30 minutes | 2 | Alex Ewert | 20 minutes | 100
Create c-unit tests | 2 hours | 1 | Chandler Miller | 1 hour | 25
Risk: 1 = lowest; 5 = highest
Version Control: Git
Project Team: Chandler Miller, Alex Ewert, Brandon Grothe, Samuel Lewis